## Slide 1
Helping you to manage projects more effectively
Project Management Toolkit

## Slide 2
Contents
Introduction to
Project Management
Templates and Guidance
Introduction and Context 3
Project Lifecycle 6
Project Management Principles 7
Roles and Responsibilities 9
Stage 1: Concept 11
Stage 2: Initiation & Planning 12
Stage 3: Delivery 13
Stage 4: Evaluation & Closure 14
Glossary 15

## Slide 3
Introduction and Context
This toolkit helps demystify the technical language that surrounds project management. As well as providing templates and guidance, it provides links to some of the resources you can access to give you confidence to initiate, lead or take part in projects within the council. It can be scaled up or down according to the size and complexity of the project, and staff in the Corporate PMO can provide advice and guidance to support you with this. It can also be used for focused task and finish pieces of work.
Projects vary in size and complexity. Having an agreed approach to project management means we are able to standardise and structure our projects so that they are managed and delivered in a consistent way across the council. This helps focus all projects in the same way and allows us to repeat successful aspects and learn from mistakes, resulting in a continuous improvement process.
Who this is for?
Anyone who would like to learn more about project management, and use these tools to support their work and particularly those who:
Manage projects and programmes i.e. Project Manager, Programme Manager
Support projects and programmes i.e. Project Support Officer
Manage projects as part of their role
Are a project/programme sponsor or SRO
Why do we need a project management approach?

## Slide 4
Projects progress in a completely different way to normal business operations and can be challenging for organisations.
By having a consistent approach to project management and a standard process and templates, the intention is that some of the below common factors to unsuccessful projects are overcome:
Lack of clear mandate.
Poor leadership (from the SRO/Board).
Poor definition of the how and why.
Poor planning.
Lack of appropriate skills and/or experience.
Lack of understanding of roles and responsibilities.
Customers not placed at the heart of project focus and decision making.
Insufficient engagement by senior management.
Lack of positive communication and engagement with stakeholders.
Unrealistic timescales.
Unrealistic budget.
Poor risk identification and management.
Lack of change management control.
Why do projects fail?

## Slide 5
A project is a unique piece of work intended to deliver planned objectives. It has a start and end date, a set of tasks that are completed in sequence, may have a dedicated budget, has a clear scope and objectives, a risk register and should articulate what the desired outcomes are. It can vary in size and complexity.
A programme is a group of projects that are similar or related to one another, and which are managed and coordinated as a group instead of independently. It has a clear scope and objectives and should articulate what the desired outcomes are for the programme as a whole. Each project within the programme assists in meeting those objectives.
A portfolio is a group of different programmes and/or projects within the same organisation, which may be related or unrelated to one another. Portfolio management includes the selection and prioritisation of programmes which are aligned with the organisation’s strategy and objectives.
What’s the difference between a Project, Programme and Portfolio?

## Slide 6
Project Lifecycle
Project management is often managed in phases or stages to improve control and quality. This means a large project is broken down into more manageable stages, each with a specific deliverable, and undertaken in a specific sequence.
At the end of each stage, a review is typically carried out on the deliverables and the performance of the project. This helps the project team come to a view as to whether the project proceeds to the next stage or undergoes revision.
Altogether, the stages of a project are known as the project lifecycle.
To find out more about each of the stages, and the templates and guidance available, please click on the relevant stage in the diagram to the right.
Stage 1:
Concept
Stage 2:
Initiation & Planning
Stage 3:
Delivery
Stage 4:
Evaluation & Closure

## Slide 7
Each project must have a clear need, a defined customer, realistic benefits and a detailed cost assessment. Projects must be aligned to the business objectives of the Council and must always be grounded in a business case.
The project must learn from the successes and mistakes from previous projects and ensure that knowledge gained throughout the project is captured and passed on to future projects.
Continued Business Justification
Learn from Experience
Define Roles and Responsibilities
The 7 Project Management Principles
Projects must have an explicit project management team structure, which consists of well-defined roles and responsibilities. Everyone should know what they are responsible for and what others involved in the project are responsible for.
Manage by Stages
Projects should be broken down into discreet components, called stages, with periodic reviews to record lessons learnt and confirm the project is still on track to meet its objectives.
PRINCE2 principles provide a standard set of behaviours to help guide the project management approach and should be applied to every project as below:

## Slide 8
Manage by exception
Project teams should keep a constant focus on the quality of the project’s products (deliverables), ensuring they are delivered at the right level of quality within the agreed cost and time constraints.
Focus on Products
Project management methods should be adjusted to suit the needs of each project, changing the amount of oversight and planning to fit the size and complexity of the project.
Since board members are typically senior managers or executives who don’t have time to manage a project's daily activities, they establish baseline requirements for things like time, cost, risk and scope and then delegate daily oversight to the project manager. The project manager has the authority to get the project back on track if it's running late or going over budget, but if issues arise that will impact the established requirements, that’s an “exception” and the project board should decide the best way to proceed.
The 7 Project Management Principles continued…
Tailor to Suit the Project

## Slide 9
Role​ | Responsibilities​
Senior Responsible Officer​ | Ensuring that the project meets its objectives and delivers the expected benefits​ Making key business decisions for the project​ Approving the project budget​ Ensuring availability of resources​ Approving changes to the project scope​ Providing additional funds for scope changes​ Approving project deliverables​
Project Manager​ | Developing a project plan​ Managing deliverables according to the plan​ Assembling and managing the project team​ Managing stakeholder communication and engagement​ Delivering successful project outcomes​ Managing project constraints including cost, time, scope, quality, risk and resources.​
Business Analyst​ | Utilised at multiple points​ Assisting in defining the project​ Gathering technical and business requirements ​ Undertaking, process mapping and re-engineering, service design​
Project Team Member​ | Contributing to overall project objectives​ Completing individual deliverables​ Providing expertise in their subject matter​
Roles and Responsibilities

## Slide 10
Templates and Guidance

## Slide 11
Templates & Guidance
Strategic Outline Business Case and Guidance
Prioritisation Guidance and How to Guide
Other Resources
Link to Change Advisory Board page once up and running
Stage 1: Concept/ Starting up a Project
This stage of project management marks the beginning of the project. Once the project idea or purpose is decided, the first stage is to map out the concept and consider ideas for change. Usually, some research is required, and this can involve consultation with colleagues and shareholders. Two key questions that need to be asked are: is it feasible and is it of value?
Other aspects to consider at this stage are the cost and project timeline, as well as the impact of the end result.
New projects must demonstrate that they provide strategic value. The prioritisation guidance provides a simple guide on how to do this.
This is all brought together in a strategic outline business case which goes forward to the Change Advisory Board and which acts as the approval gateway. They will consider all business cases and decide if the project or programme is aligned to strategic priorities and will recommend that the project is initiated.
The project then progresses to Stage 2: Initiation and Planning.

## Slide 12
Stage 2: Initiation & Planning
Templates & Guidance
Project Initiation Document:
  Project Plan
  Change Control Approach
  Communication and Engagement Approach and Guidance
Project Initiation Document Guidance
Benefits Realisation Plan and Benefits Management Guidance
Risk register and Risk Management Guidance
Board Terms of Reference
Other Resources
Link to Benefits Management e-learning module​
The second stage is defining and planning the project, from mapping out the scope to developing a project plan and working out the cost, which includes deciding on the staffing resources needed and budget calculation. All of this information is captured in the Project Initiation Document (PID)
This is also where:
risks are identified and planned for;
stakeholders are identified and their level of interest assessed through stakeholder mapping;
a stakeholder communications and engagement plan is developed;
the project team and project governance is established; and
the cashable and non-cashable benefits are profiled and mapped and a Benefits Realisation Plan is developed.
As with any stage of a project, changes may occur, so remember to build in contingency plans to allow for delays.
The project then progresses to Stage 3: Delivery

## Slide 13
Stage 3: Delivery
Templates & Guidance
Board Agenda
Board Action Tracker
Highlight Report
Change Control and Change Control Guidance
Lessons Learnt Log
Issues Register and Issue Management Guidance
Other Resources
Link to Change Advisory Board page once up and running​
Once the project has been agreed, the project moves into the delivery stage. Teams established in Stage 2 meet to learn the project timelines, tasks are assigned, resources are distributed, and other information related to the project is imparted. The Project Manager ensures that every team member knows what they need to do, and by when, and manages the project constraints including cost, time, scope, quality, risk and resources. The Senior Responsible Officer ensures that the project meets its objectives and delivers the expected benefits.
The frequency of monitoring a project’s progress against quality, time and cost/budget is agreed and monitoring reports are provided as required. Benefits are also tracked, monitored and reported on at the agreed frequency.
Occasionally things go wrong or unexpected delays are encountered. An issues register should be created to record any issues and actions taken. If an issue results in any changes to the baseline of the project, a Change Control document is developed and taken to the project board for approval. Where there is a significant impact to the project’s budget, benefits realisation, timelines or staffing resources, the Change Control should also be taken through the Change Advisory Board.
Any lessons learnt should be logged in the lessons learnt log as the project progresses rather than waiting until the end of the project.

## Slide 14
Stage 4: Evaluation & Closure
Templates & Guidance
Project Closure Report
Programme Closure Report
Other Resources
This stage is where an analysis of completed objectives and activities is carried out to determine whether the project has produced the planned results, delivered the expected benefits and made the desired change. Projects should be evaluated before a decision is made to close the project down. The change is deemed business as usual (BAU), stakeholders are told of the completion of the project and all resources are released.
If a stand alone project or workstream within a progamme is being closed down the project closure template should be used; if a programme is being closed down the programme closure report should be used.
The project manager can analyse the project scope. This includes the quality of the work, whether it was completed on time and any internal or external problems
The Lessons Learnt log is finalised, any contracts with suppliers are terminated and a final budget and project report is produced. All relevant documentation is collated and filed.
Any cashable or non-cashable benefits which are expected to be realised after project closure are handed to business owners and tracking/reporting of them is agreed.

## Slide 15
Helping you to manage projects more effectively
What templates do I need to use?
As a project or a programme manager, you will be expected to use the following templates as a minimum:
Project Manager:
Strategic outline business case
PID
Risk log
Issues log
Benefits Realisation Plan
Highlight report
Programme Manager
All the above plus:
Programme Plan
Workstream delivery plans
If you manage projects as part of your role and would like advice on which templates you should use, please contact the PMO via the contact details on slide 22

## Slide 16
Glossary
Assumption
A statement that is taken as being true for the purposes of planning where some facts are not yet known or decided and may cause considerable replanning.
Assurance
All the systematic actions necessary to provide confidence that the target (e.g. system, process, organisation, programme, project, outcome, benefit, capability, product output or deliverable) is appropriate. Appropriateness might be defined subjectively or objectively in different circumstances. The implication is that assurance will have a level of independence from that which is being assured.
Baseline
Reference levels against which an entity is monitored and controlled.
Benefit
The measurable improvement resulting from an outcome perceived as an advantage by one or more stakeholders and which contributes to organisational/strategic objectives. Benefits can be tangible (e.g. money saved, jobs created) or intangible (e.g. corporate reputation) and quantifiable in financial terms (e.g. reduced costs) or non-financial terms (e.g. greater customer satisfaction). A dis-benefit is the measurable result of a change, perceived as negative by one or more stakeholders, which detracts from one or more organisational/strategic objective.

## Slide 17
Glossary
Business Case
The justification for a project, which typically contains timescales, costs, benefits and risks, and against which continuing viability is tested.
Change Authority
A person or group which considers requests for change or off-specifications.
Change Control
The process through which all requests to change the approved baseline of a project are identified, assessed and then approved, rejected or deferred.
Dependency
The relationship between products or tasks, i.e. tasks that require input from other tasks to be completed, or activities that cannot start until a previous activity is done.
Deliverable
Project deliverables are specific measurable end results that you are aiming to produce at specific points during the project. They are sometimes referred to as products.

## Slide 18
Glossary
Exception
A situation where it can be forecast that there will be a deviation beyond the tolerance levels.
Governance
The management framework within which project decisions are made, which can include project workstreams, steering group and a project board.
Highlight Report
A time-driven report from the project manager to the project board reporting progress against delivery.
Issue
A relevant event that has happened, was not planned, and requires management action.
Lessons Log
An informal repository for lessons that apply to this project or future projects.
Milestone
A significant event in a plan’s schedule, such as completion of key work packages, a development step or a management stage.

## Slide 19
Glossary
Objective
Objectives define the desired benefits, outcomes or performance improvements that you expect from the project. Objectives are likely to start with the word 'to', and contain words like 'increase', 'improve', 'reduce'.
Outcome
“What difference does the project make?” The changes that occur as a result of the project.
Output
“What do you get out of the project?” Tangible items produced as a result of the project.
Project Lifecycle
The sequence of stages through which a project progresses. It includes initiation, planning, delivery, evaluation and closure.
Project Plan
A formal, approved document used to guide both project delivery and project control. It articulates how and when a project's objectives are to be achieved, by showing the major products, milestones, activities, and resources required on the project.

## Slide 20
Glossary
Risk
An uncertain event or set of events that, should it occur, will have an effect on the achievement of objectives. A risk is assessed by a combination of the probability of a perceived threat occurring, and the magnitude of its impact on objectives.
Risk Owner
A named individual who is responsible for the management, monitoring and control of all aspects of a particular risk assigned to them.
Risk Register
A record of identified risks and mitigating actions relating to a project.
Scope
Project scope is a detailed outline of all aspects of a project, including all related activities, resources, timelines, and deliverables, as well as the project’s boundaries. A project scope also outlines key stakeholders, processes, assumptions, and constraints, as well as what the project is about, what is included, and what isn’t.

## Slide 21
Stakeholder
Any individual, group or organisation that can affect, be affected by or perceive itself to be affected by an initiative (i.e. a programme, project, activity or risk).
Tolerance
The permissible deviation above and below a plan’s target for time and cost without escalating the deviation to the next level of management. There may also be tolerance levels for quality, scope, benefits and risk.
Tranche
A programme management term describing a group of projects structured around distinct step changes in capability and benefit delivery.
User Acceptance
A specific type of acceptance by the person or group who will use the product after it has been handed over into the operational environment.
Glossary

## Slide 22
Advice and Guidance
You can contact a member of the PMO Team on the following email address:
CorporatePMO@sthelens.gov.uk
Team Members:
Davinder Gill, Corporate PMO Manager
DavinderGill@sthelens.gov.uk
Mark Hibbard, Programme Manager
MarkHibbard@sthelens.gov.uk
Lindsay Ogden-Dabbs, Programme Manager
LindsayOgdenDabbs@sthelens.gov.uk
Jordan Stead, Graduate Policy and Transformation Officer
JordanStead@sthelens.gov.uk