## Tiering
| Criteria | 0 | 3 | 6 | 9 | Score
Finance | Finance - Savings | No financial impact to the organisation | Low financial impact to the organisation up to £500k | Moderate financial impact to the organisation between £500k - £1million | Significant financial impact to the organisation, more than £1 million | 9
| Finance - cost of project | 0 | Up to £500k | £500k - £1 million | More than £1 million | 9
| Finance - Funding the Project | Achievable within budget | £0-£500k Investment required | £500k + Investment required | External funding being provided/required | 9
Risk | Risk – Level of risk for not completing the project | No risk involved | Low risk to the organisation if not provided | Moderate risk to the organisation if not provided | Essential / critical to the customer/organisation | 0
| Risk – What is the level of risk included in the project? (Political, Financial, Reputational) | No Risk | Low Risk | Moderate Risk | Significant Risk | SELECT
Stakeholder | Stakeholders – Wards | No impact of change on wards | Single ward | Two or more/ Community panel footprint | Cumberland footprint | SELECT
| Stakeholders – What is the impact on internal stakeholders? | No / Minimal impact on internal stakeholders | Team | Directorate | Full council | SELECT
Input | Inputs – What is the anticipated resource required for the project? | No additional resource and capacity required from the service | Resource within the service only | Ad hoc resource required from 1or 2 other enabler departments | Full time resource required from other departments / Consultant required | SELECT
RESULT | Total Project Score |  |  |  |  | 27
| Project Priority | 0 – 12 BAU 13-35 Improvement Engine 36-53 Service Level 53-72 Corporate Level |  | Result: | Improvement Engine

## Key Information
Aims of Cumberland Council
Addressing inequalities,
Local economies that work for local people,
Environmental resilience and the climate emergency
Delivering excellent public services
Impact on the factors that improve health and wellbeing.

## Prioritisation
| Criteria | 0 | 1 | 2 | 3 | 4 | Score | Weighting | Weighted Score | Comments / Justification
Achievement of objectives | Meeting Council Strategic Objectives | Delivers no progress towards Council strategic objectives | Delivers low and/or less measurable progress towards Council strategic objectives | Delivers moderate measurable progress towards Council strategic objectives | Delivers high, but hard to measure progress or moderarte measurable progress towards Council strategic objectives | Delivers high, specific and measurable progress towards Council strategic objectives | SELECT | 1
| Alignment to design principles | Not aligned to design principles | Alignment to one or two design principles | Alignment to three to four design principles | Alignment to five to six design principles | Well aligned to seven or eight design principles | SELECT | 1
Delivery | Change | Very significant change is required. Very Significant effect on ongoing services. | Significant change is required. Significant effect on ongoing services. | Moderate change is required. Significant effect on ongoing services. | Moderate change is required. Moderate effect on ongoing services. | Little to no change is required. Little to no effect on ongoing services. | SELECT | 1
| Capacity | No delivery capacity. | Very low delivery capacity. | Low delivery capacity. | Moderate delivery capacity. | High delivery capacity. | SELECT | 1
| Capability | No delivery capability. | Very low delivery capability. | Low delivery capability. | Moderate delivery capability. | High delivery capability. | SELECT | 1
Resource | Cost Impact | No or low ROI | Moderate ROI. Limited evidence. | Moderate ROI. Robust evidence. | High ROI. Limited evidence | High ROI. Robust evidence. | SELECT | 3
| Affordability / Funding | Cost of the project is not affordable for the Council | Cost funded through borrowing | Cost met from transformation fund / EFS | Cost met from existing budget | Externally funded | SELECT | 1
| Productivity and Demand on Staff | Low productivity gain / Little demand reduction on staff. | Moderate productivity gain / Moderate demand reduction on staff. Limited evidence. | Moderate productivity gain / Moderate demand reduction on staff. Robustly evidenced. | High productivity gain / Substantial demand reduction on staff. Limited evidenced. | High productivity gain / Substantial demand reduction on staff. Robustly evidenced. | SELECT | 1
Risk | Risk – Level of risk for not completing the project | No risk involved | Low risk to the organisation if not provided | Moderate risk to the organisation if not provided | High risk to the organisation if not provided | Essential / critical to the organisation | SELECT | 1
RESULT | Total Project Score | [5 empty] | 0 |  | 0