## Mini Guide
[5 empty] | Internal Ref: | Project Management Toolkit Mini Guide to Managing Change
[5 empty] | Next Review Date | 2023-11-01
[5 empty] | Version No. | 1
A MINI GUIDE TO MANAGING CHANGE IN PROJECTS
This guide outlines how to assess and act upon issues which have a potential impact on any of the baseline aspects of the project - the plans or final product.
Overview
Change is inevitable during the life of a project, so a systematic approach to identifying, assessing and controlling issues that may result in
change is vital. Changes may arise from project team members, stakeholders, complaints or any manner of factors and must be managed to
ensure that the projects performance targets (time, cost, quality, scope, risk and benefits) are not compromised.
The aim of issue and change control procedures is not to prevent changes: it is to ensure that every change is agreed by the relevant
Authority (governance) before it takes place. This means that a prerequisite of effective issue and change control is to have a robust baseline in
place on the Full Business Case to ensure that the correct outputs are delivered to the Client.
What is an Issue?
To clarify an issue is defined as something which has already happened, wasn’t planned and requires managerial action. This differs from a risk
which is something which hasn’t happened yet and there is uncertainty around it.
Issues may be raised at any time during a project and include the following types
| Types of Issue |  | Definition
| Request For Change (RFC) |  | The User/Client changes their mind or the Supplier suggests a better way
| Off-Specification |  | Something that should be provided by the project but currently is not or is forecast not to be provided.
| Problem/Concern |  | Any other issue that the PM needs to resolve or escalate
An Issue Log (Doc 7.2 in the Toolkit) is provided to capture and maintain information on all of the issues that are being managed formally. It
should be completed when an issue has occurred and monitored by the Project Lead on a regular basis. This will provide an audit trail of any
authorised changes throughout the life of the project.
Issue and Change Control Process
Step 1: CAPTURE
The first step in the process is to undertake an initial analysis to determine that type of issue that's been raised and whether it can be managed informally or formally. This will ensure that decisions are made at an appropriate level withing the team, avoid inundating senior management with too many issues and reduce the administrative burden on the Project Lead. Issues being managed formally should be determined by issue type and by severity/priority and captured on the Issue Log.
Step 2: EXAMINE
The next step is to examine the issue by undertaking an impact analysis. The Project lead should look at - the project performance targets in terms of cost, time, quality and scope - the business case in terms of the impact on benefits - the impact on the overall risk to the project - the impact on a programme if the project is part of one
Step 3: PROPOSE
Having gained a full understanding of the impact of the issue, the next step is to consider alternative options for responding to it and proposing a course of action to take. The Project Lead should consider the effect each option will have on the project's time, cost, quality, scope, benefits and risk performance targets.
Step 4: DECIDE
The Project Lead may be able to resolve an issue without the need to escalate it to the Project Board or equivalent, for example if the issue is a minor change which doesn't affect anything else in the project. Other issues might have to be escalated to the Project Board or equivalent for a decision using an Exception Report ( Doc7.3 in the Toolkit)
Step 5: IMPLEMENT
The Project Lead will either - take corrective action themselves for a minor issue, or - complete the Exception Report for approval by the Project Board or equivalent. The Project Board or equivalent can approve, reject, defer, request more information or may just provide guidance. The decision and those authorising it must be recorded on the Issue Log and a reference made on the Full Business Case as to the authorised changes to the project's time, cost, quality, scope, benefits and risk performance targets.
How to prioritise issues
There are numerous ways to prioritise issues, one of which is called MoSCoW
|  | Must have |  | The change is essential for the viability of the project
|  | Should have |  | The change is important and its absence weakens the Business Case
|  | Could have |  | The change is useful but its absence does not weaken the Business Case
|  | Won't have (for now) |  | The change is not essential nor important and can wait.

## 7.2 Issue Log
[9 empty] | Internal Ref: | Project Management Toolkit Doc 7.2. Issues Log Generic
[9 empty] | Review date | 2025-02-01
[9 empty] | Version No. | 7
7.2 Issues Log
Complete this document to capture and maintain information on all issues that are formally managed during the project.
Project Name |  | Spa La La
Project Lead |  | Spa La La
Issue No. | Date Raised | Project Stage | Raised By | Issue Type | Description of Issue | Impact | Recommendation | Decision |  | Authorised By | Date
[8 empty] | Project Lead Action | Escalate to Project Board on Exception Report

## Sheet1
Request for Change
Off Spec
Problem or Concern