## Benefits Mgt - Process Flow (hidden)
Guidance Documents:
 Benefits Management Framework |  Procedure Guidance - Benefits Assessment Workshop
 Procedure Guidance - Create a Benefits Map |  Procedure Guidance - Stakeholder Feedback Form
Benefits Management - Process Flow

## Definitions & Values
Definitions and Values
Benefit ID – A unique identifer or number for each benefit entered | Benefit Owner – The individual responsible for measuring benefit progress, and accomplishing the benefit objective.
Primary Benefit Category - What is the largest and most important benefit to be achieved? o Cost Avoidance = realisation of benefit enables the business to avoid incurring additional costs in the future/avoids increase in budget o Cost Reduction = realisation of benefit will reduce costs to the business/reduces budget o Efficiency = realisation of benefit will reduce the amount of resource effort to produce a given output o Improved Security = realisation of benefit will maintain integrity and protect council and citizen assets (people/data/finance/property) o Improved User Experience = realisation of benefit will improve the satisfation and overall perception of value of "X" product/process/system o Procurement Compliance = realisation of benefit will ensure that the council maintains compliance to procurement policy, e.g. maximum contract terms, and ensures maximisation of value o Legislative/Regulatory Compliance = realisation of the benefit will deliver compliance to law (legislation/statute) and the method for monitoring and enforcement thereof (regulation) o Reputation = realisation of this benefit will improve relationships through confidence and trust, attracting loyalty, investment and collaboration o Risk Avoidance = realisation of this benefit will eliminate exposure to a potential loss o Risk Reduction = realisation of this benefit will reduce the likelihood and severity of a possible loss | Stakeholders and Beneficiaries – Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Measure Description – What measurement will be used to gauge progress and success in achieving the benefit?
Baseline Measure – What was the value of the measure before work started? Target Measure – What is the target value of the measure once the work is completed?
Planned Outcome – What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”)
Realised Measure – What is the realised/actual measured result(s) now the work has been completed?
Expected Realisation Date – Year and month originally planned for completion of Planned Outcome.
Actual Realisation Date – Date of completion of the Planned Outcome/Benefit. If the full benefit is no longer expected, enter N/A.
Status – High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o Realised = Benefit has been realised. Actual result matches expected. o On Track = On Schedule for realising benefit. o Warning = Some risk towards realising benefit. o Critical = Benefit realisation will not be met. o N/A = Benefit no longer applies.

## Benefit Profile & Realisation
IRN: pmo104-v1.0
Project No.:
Project Name:
Project Manager Name:
SRO Name:
BENEFITS PROFILE | [12 empty] | BENEFITS REALISATION PLAN | [6 empty] | BENEFITS TRACKER (Forecast and Actual Benefits)
Objective/Benefit ID | Benefit Title | Date Benefit Identified | Identified at | Primary Benefit Category | Benefit Description | Benefit Owner (Department) | Benefit Owner | Benefit Type (Financial/Non Financial) | Measure Description | Baseline Measure | Target Measure | Realised | Planned Outcome | Stakeholders and Beneficiaries | Realised Measure | Status | Expected Realisation Date | Actual Realisation Date | Comment/Update | Period 1 (Month 1) |  | Period 2 (Month 2) |  | Period 3 (Month 3) |  | Period 4 (Month 4) |  | Period 5 (Month 5) |  | Period 6 (Month 6)
[20 empty] | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits
AR Objective 1.0 | Account Receivable Cost Reduction (Licence cost, print cost, FTE) | 2024-07-05 | Stakeholder Workshop | Cost Reduction | Reduce expenses at the end of each month | AR, CCC | LF | Financial | The financial level of debts at the end of each calendar month (£m) | 2 | 1 | Realised | Send 80% of Invoices and reminder letters via Email | AR (NNC/CCC/MKC/WNC) | TBC | On Track | 2024-06-30 | 2024-06-01 |  | 1 | 2 | 1 | 2 | 1 | 1.55 | 1 | 1.45 | 1 | 1.15 | 1 | 1
AR BEN 1.2 | Reduced print costs on recovery letters | 2024-07-05 | Stakeholder Workshop | Cost Reduction | Reduction in the total number of paper invoices/recovery letters produced monthly/annually | AR MKCC,CCC,WNC | LF,CF,VF | Financial | Number of recovery letters issued each calendar month (No) | 200k | 50k | Realised | [7 empty] | £200k | £195k | £180k | £190k | £150k | £120k | 100 | 100 | £50k | £75k | £50k | £50k
AR Objective 2.0 | Account Receivebale reduce capacity | 2024-07-05 | Stakeholder Workshop | Risk Reduction | Reduction in resource time spent producing portfolio | AR, CCC | LF | Financial | Level of effort expressed per hour/day to manage protfolio (days) | 20 | 19 | Realised
AR BEN 2.1 | Reduction in the level of effort to run debt reports | 2024-07-05 | Stakeholder Workshop | Risk Reduction | Real time reporting and case management | AR MKCC,CCC,WNC | LF,CF,VF | Financial | Total number of hours to build a report (hours/day) | 2-4hrs | .5hr | Realised
BusSys Objective 3.0 | Improve and reduce manual bank rec processes | 2024-07-05 | Stakeholder Workshop | Risk Reduction | To reduce the number of unreconciled payments tranferred to service areas for resolution. | AR MKCC,CCC,WNC | LF,CF,VF | Financial | Number of Halo request/incident resolved by Bank rec team (no per year | 600 | 200

## RACI Matrix
RACI Matrix - Benefit Realisation Plan
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Activities | Roles
|  | SME (Service Area) | SRO | PROJECT MANAGER/BCA | PMO
1 | Define Success (Prospect Stage)
1.1 | Align strategic objectives with Business Plan (Business Challenges) | R | A | - | C
1.2 | Identify and prioritise project objectives (Prospect approved and PM assigned) | C | I | R | I
1.3 | Change driver Analysis | C | I | R | I
1.4 | Identify desired outcomes | C | I | R | I
1.5 | Identify key stakeholders | C | C | R | I
2 | Identify and Quantify
2.1 | Identify Benefits | C | I | R | I
2.2 | Prioritise Benefits | C | I | R | I
2.3 | Categotise Benefits | C | I | R | I
2.4 | Identify measures and quantify benefits | C | I | R | C
3 | Value and Appraise
3.1 | Model benefits for OBC | C | I | R | I
3.2 | Identify benefit dependencies | C | I | R | I
3.3 | Outline roles and responsibilities | C | I | R | I
3.4 | Identify benefit dependencies and risks | C | I | R | I
3.5 | Outline measurement and reporting arrangements | C | I | R | I
3.6 | Review, refine and prioritise benefits | - | - | R | C
4 | Plan to Realise
4.1 | Finalise cost benefits measurements | C | I | R | I
4.2 | Track Benefits | R | I | R | C
4.3 | Manage change and impact | R | I | C | -
5 | Work to Realise
5.1 | Work with Benefits Owners to transition to BAU | C | I | R | -
5.2 | Formally sign off benefits responsibility to Benefit Owners | R | A | R | C
5.3 | Measure, Track and Reports benefits | - | - | R | R
5.4 | Agree actions for further benefits realisation |  |  | R
5.5 | Agree and document plan for Post Implementation Handover (closure reports) | C | A | R | I
6 | Post Project Review Performance
6.1 | Review benefits realisation to date against plan | - | - | - | R
6.2 | Present Post Implementation Review (PIR) findings to relevant board | - | - | - | R
6.3 | Review lessons learned document | - | - | - | R

## Lists (hidden)
State | Status | Primary Benefit Category | Identified at | Benefit Type
Active | Realised | Cost Avoidance | Benefits Workshop | Financial
Future | On Track | Cost Reduction | Stakeholder Workshop | Non Financial
| Warning | Efficiency | Project Team Review
| Critical | Improved Security | PDG
| N/A | Improved User Experience | Project Board
|  | Procurement Compliance | Bus Systems Board
|  | Regulatory/Legislative Compliance | Other
Reputation
Risk Avoidance
Risk Reduction

## PMO Change Control (hidden)
PMO Change Control
IRN: pmo104 v1.0
IRN | Version Updated | Date Updated | Version updated to: | Updated by: | Details of Change

## Benefit Measure Tracker (hidden)
Project No.:
Project Name:
Project Manager Name:
SRO Name:
| Actuals to Date |  |  |  |  | Forecast and Actual Benefits
Objective/Benefit ID | Benefits | Beneft Owner | Benefit Measure | Baseline Value | Target Value | Period 1 (Month 1) |  | Period 2 (Month 2) |  | Period 3 (Month 3) |  | Period 4 (Month 4) |  | Period 5 (Month 5) |  | Period 6 (Month 6)
[6 empty] | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits | Forecast Benefits | Actual Benefits
|  | The person responsible for delivering and reporting the benefit | What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success? | What was the value of the measure before project started? | What was the targte value of the measure one the work stated? | Expected Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Actual Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Expected Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Actual Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Expected Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Actual Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Expected Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Actual Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Expected Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Actual Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Expected Benefit Outcome over a specific target period (Monthly, 3 months, 6 months) | Actual Benefit Outcome over a specific target period (Monthly, 3 months, 6 months)
AR BEN 1.1 | Reduction in time to recover debts | Owner A | Duration between invocie trigger and cash receipt (Days) | 10 days | 6 days | 9 | 10 | 9 | 8 | 8 | 8 | 6 | 8 | 7 | 6 | 6 | 6
AR BEN 1.2 | Reduced print costs on recovery letters | Owner A | Number of recovery letters issued each calendar month (No) | 1000 | 200 | 1000 | 900 | 900 | 800 | 700 | 400 | 350 | 400 | 350 | 400 | 350 | 200
AR BEN 1.3 | Reduction in the level of effort to run debt reports | Owner A | Total number of hours to build a report (hours/day) | 4hr | .5hr | 4hr | 3hr | 4hr | 3hr | 3hr | 2.8hr | 3hr | 2hr | 2hr | 1.5hr | 1hr | .5hr
Example

## Post-Project Benefits Tracker (hidden)
Post-Project Benefits Tracking
Project No.: |  | 0
Project Name: |  | 0
Project Manager Name: |  | 0
SRO Name: |  | 0
Benefit ID | Primary Benefit Category | Benefit Description | Requestor | Benefit State | Benefit Owner | Planned Outcome | Stakeholders and Beneficiaries | Measure Description & Expected Result | Baseline Measure | Target Measure | Measure Frequency | Realised Measure | Status | Expected Realisation Date | Actual Realisation Date | Comment/Update
BEN-P001 | [16 empty] | On Track
BEN-P002 | [16 empty] | Warning
BEN-P003 | [16 empty] | Critical
BEN-P004

## Role Definitions (hidden)
Role Definitions
Responsible
Those who do the work to achieve a task. There is typically one role with a participation type of Responsible.
Accountable
Those who are ultimately accountable for the correct and thorough completion of the deliverable or task, and the one to whom Responsible is accountable. Typically, the Process Owner is Accountable for a process, and there must be only one Accountable specified for each task or deliverable.
Consulted
Those who are not directly involved in a process but provide inputs and whose opinions are sought.
Informed
Those who receive outputs from a process or are kept up-to-date on progress, often only on completion of the task or deliverable.
Process Areas
Service Strategy
The objective of Service Strategy is to decide on a strategy to serve customers. Starting from an assessment of customer needs and the market place, the Service Strategy lifecycle stage determines which services the organization is to offer and what capabilities need to be developed. Its ultimate goal is to make the organization think and act in a strategic manner.
Service Design
The objective of Service Design is to design new services. The scope of the Service Design lifecycle stage includes the design of new services, as well as changes and improvements to existing ones.
Service Transition
The objective of Service Transition is to build and deploy services. The Service Transition lifecycle stage also makes sure that changes to services and service management processes are carried out in a coordinated way.
Service Operations
The objective of Service Operation is to make sure that services are delivered effectively and efficiently. The Service Operation lifecycle stage includes the fulfilling of user requests, resolving service failures, fixing problems, as well as carrying out routine operational tasks.
Continual Service Improvement
The Continual Service Improvement (CSI) process uses methods from quality management in order to learn from past successes and failures. The CSI lifecycle stage aims to continually improve the effectiveness and efficiency of processes and services, in line with the concept of continual improvement adopted in ISO 20000.

## RACI - Highlevel (hidden)
RACI Matrix - Benefit Management Cycle
High Level Activities
|  |  | BCA | PROJECT MANAGER | PMO | Service Area
| 1 | Define Success | R | A | C | I
| 2 | Identify and Quantify | R | A | C | C
| 3 | Value and Appraise (Establish baseline metrics) | R | A | C | C
| 4 | Plan to Realise (Develop Benefits Realisation Plan) | A | R | C | I
| 5 | Work to Realise (Monitor, track and reports on Benefits Realisation) | C | R | A | I
| 6 | Review Performance and Optimise Benefits | C | R | A | I
| 7 | Conduct Post implementation review | C | R | A | I
| 8 | Conduct Stakeholder Engagament | C | A | A | C
| 9 | Transition to BAU | I | A | C | R
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable

## RACI - Service Strategy (hidden)
RACI Matrix - Income Management
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Task | Roles
|  | Head of Enterprise Applications | Service and Support Mananger | Environment & Supplier Manager | System Change & Engagement Manager | Compliance & Improvement Manager | Business Systems Manager | Functional Development Manager | Functional Analyst | HeyCentric | Head of Procurement | Head of Audit | Head of Customer Engagement, Business Development & Performance | DTI | Head of Business Planning and Finance | BSCPMO | Legal | Treasury | Business
1.1 | Strategy Management
1.1.1 | Strategy Management | A | R | I | I | I | R | I | I |  |  |  |  | C |  | I |  |  | C
1.1.2 | Demand Management | A | R |  |  |  | R |  |  | R
1.1.3 | Service Portfolio Management | A | R |  |  |  | R |  |  | R
1.1.4 | Financial Management | A | R |  |  |  | C
1.2 | Demand Management
1.2.1 | Identifying sources of demand and forecasting |  | A | R | R |  |  | R |  | R
1.2.2 | Analysing the patterns of business activity and user profiles |  | A | R | R |  |  | R |  | R
1.2.3 | Developing differentiated offerings
1.2.4 | Managing operational demand |  | A | R | R |  |  | R |  | R
1.3 | Service Portfolio Management
1.3.1 | Defition of the services | A | R | C | C |  | R |  |  | C
1.3.2 | Analysis of the services | A | R | C | C |  | R |  |  | C
1.3.3 | Approval | A | R | C | C |  | R |  |  | C
1.3.4 | Chartering of services | A | R | C | C |  | R |  |  | C
1.4 | Financial Management
1.4.1 | Budgeting
1.4.2 | Accounting
1.4.3 | Charging
1.5 | Business Relationship Manager
1.5.1 | Request and complaints handling
1.5.2 | Opportunity identification
1.5.3 | Managing business relationships

## RACI - Service Design (hidden)
RACI Matrix - Income Management
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Task | Roles
|  | Head of Enterprise Applications | Service and Support Mananger | Environment & Supplier Manager | System Change & Engagement Manager | Compliance & Improvement Manager | Business Systems Manager | Functional Development Manager | Functional Analyst | HeyCentric | Head of Procurement | Head of Audit | Head of Insurance | Head of Customer Engagement, Business Development & Performance | DTI | Head of Business Planning and Finance | BSCPMO | Legal | Treasury
2.1 | Service Catalogue Management
2.1.1 | Documenting Service Definition and Description
2.1.2 | Agreeing Service Catalogue Contents
2.1.3 | Producing Service Catalogue
2.1.4 | Maintaining Service Catalogue
2.2 | Availability Management
2.2.1 | Monitoring availability
2.2.2 | Analyse Availability Data
2.2.3 | Investigating Service unavailability
2.2.4 | Availability Planning
2.2.5 | Review availability & testing
2.3 | Information Security Management
2.3.1 | Understanding security requirements
2.3.2 | Producing security policy
2.3.3 | Implementing security policy
2.3.4 | Assessing information assets and risks
2.3.5 | Reviewing security controls
2.4 | Service Level Management
2.4.1 | Understanding requirements and drafting SLA's
2.4.2 | Negotiating SLA's
2.4.3 | Define and standardise SLA's
2.4.4 | Monitor and report service performance
KPIs
2.5 | Capacity Management
2.5.1 | Monitor capacity and performance data
2.5.2 | Analyse the capacity data
2.5.3 | Investigate capacity issues
2.5.4 | Define and revise capacity plans
2.5.5 | Review and optimise capacity
2.6 | Design Coordination
2.6.1 | Define policies and methods
2.6.2 | Planning resources and capabilities
2.6.3 | Managing design risks
2.6.4 | Improving service design
2.7 | Supplier Management
2.7.1 | Defining requirements
2.7.2 | Evaluating suppliers
2.7.3 | Selection of suppliers
2.7.4 | Manage performance
2.7.5 | Renew or terminate contract
2.8 | IT Service Continuity
2.8.1 | Develop requirements
2.8.2 | Develop continuity plans
2.8.3 | Implement continuity plans
2.8.4 | Invoke continuity plans

## RACI - Service Transition (hidden)
RACI Matrix - Income Management
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Task | Roles
|  | Head of Enterprise Applications | Service and Support Mananger | Environment & Supplier Manager | System Change & Engagement Manager | Compliance & Improvement Manager | Business Systems Manager | Functional Development Manager | Functional Analyst | HeyCentric | Head of Procurement | Head of Audit | Head of Insurance | Head of Customer Engagement, Business Development & Performance | DTI | Head of Business Planning and Finance | BSCPMO | Legal | Treasury
3.1 | Transition Planning and Support
3.1.1 | Definition of transition strategy
3.1.2 | Preparing for service transition
3.1.3 | Planning and coordinating service transition
3.1.4 | Monitoring and reporting progress
3.2 | Change Management
3.2.1 | Registration and categorization
3.2.2 | Risk and impact analysis
3.2.3 | Approval
3.2.4 | Coordination of change build and testing
3.2.5 | Authorizae change deployment
3.2.6 | Review and close change record
3.3 | Change Evaluation
3.3.1 | Plan evaluation
3.3.2 | Evaluate prediceted performance
3.3.3 | Evaluate actual performance
3.4 | Release and deployment management
3.4.1 | Release planning
3.4.2 | Build and test release
3.4.3 | Deployment
3.4.4 | Early life support
3.4.5 | Review and closure
3.5 | Service asset and configuration management
3.5.1 | Management and planning
3.5.2 | CI Identification
3.5.3 | CI control
3.5.4 | Status accounting and reports
3.5.5 | Verification and accounting
3.6 | Service Validation and Testing
3.6.1 | Planning and designing tests
3.6.2 | Veryfing tests plands and designs
3.6.3 | Preparing test environments
3.6.4 | Performing tests
3.6.5 | Evaluating exit criteria
3.6.6 | Cleaning test environments anc closure
3.7 | Knowledge Management
3.7.1 | Defining knowledge management strategy
3.7.2 | Identify and gather data sources
3.7.3 | Draft knowledge
3.7.4 | Technical review
3.7.5 | Editorial review
3.7.6 | Publish

## RACI - Service Operations (hidden)
RACI Matrix - Income Management
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Task | Roles
|  | Head of Enterprise Applications | Service and Support Mananger | Environment & Supplier Manager | System Change & Engagement Manager | Compliance & Improvement Manager | Business Systems Manager | Functional Development Manager | Functional Analyst | HeyCentric | Head of Procurement | Head of Audit | Head of Insurance | Head of Customer Engagement, Business Development & Performance | DTI | Head of Business Planning and Finance | BSCPMO | Legal | Treasury
4.1 | Access management
4.1.1 | Access requisition
4.1.2 | Verification and validation
4.1.3 | Provision of rights
4.1.4 | Monitoring the access
4.1.5 | Deprovisioning the access
4.2 | Event management
4.2.1 | Event Notification
4.2.2 | Event detection
4.2.3 | Correlating and filtering events
4.2.4 | Categorization of events
4.2.5 | Event review and closure
4.3 | Service request fulfilment
4.3.1 | Request registration
4.3.2 | Validatiing requests
4.3.3 | Categoriza and prioritize requests
4.3.4 | Review and authorize requests
4.3.5 | Request closure
4.4 | Incident management
4.4.1 | Incident registration & categorization
4.4.2 | Prioritization
4.4.3 | Investigation and diagnosis
4.4.4 | Resolution
4.4.5 | Closure
4.5 | Problem management
4.5.1 | Problem detection and logging
4.5.2 | Categorization of events
4.5.3 | Investigation and diagnosis
4.5.4 | Resolution
4.5.5 | Closure

## RACI - CSI (hidden)
RACI Matrix - Income Management
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Task | Roles
|  | Head of Enterprise Applications | Service and Support Mananger | Environment & Supplier Manager | System Change & Engagement Manager | Compliance & Improvement Manager | Business Systems Manager | Functional Development Manager | Functional Analyst | HeyCentric | Head of Procurement | Head of Audit | Head of Insurance | Head of Customer Engagement, Business Development & Performance | DTI | Head of Business Planning and Finance | BSCPMO | Legal | Treasury
5.1 | Seven step improvement
5.1.1 | Identify the strategy for improvement
5.1.2 | Define what you will measure
5.1.3 | Gather Data
5.1.4 | Process Data
5.1.5 | Analyse information and data
5.1.6 | Present and use information
5.1.7 | Implement Improvement

## RACI - Product Specific (hidden)
RACI Matrix - Income Management
R | Responsible | Person(s) responsible for the task, who ensures that it is done.
A | Accountable | Person who is ultimately accountable and has Yes/No/Veto.
C | Consulted | Person(s) that needs to feedback and contribute to the activity.
I | Informed | Person(s) that needs to know of the decision or action.
- | Not Applicable
| Task | Roles
|  | Head of Enterprise Applications | Service and Support Manager | Environment & Supplier Manager | System Change & Engagement Manager | Compliance & Improvement Manager | Functional Development Manager (Func AR) | Functional Analyst (FUNC AR) | Business Systems Support Analyst | Business Systems Support Officer | Income (Finance Operations) | End User / Service Area | HeyCentric | DTI
6 | HeyCentric Specific
6.1 | System Maintenance
6.1.1 | Revenue Code Create/Update/Delete | - | - | - | - | - | A | - | R | - | - | - | - | -
6.1.2 | Attribute Create/Update/Delete | - | - | - | - | - | A | - | R | - | - | - | - | -
6.1.3 | Chart of Accounts Create/Update/Delete | - | - | - | - | - | A | - | R | - | - | - | - | -
6.1.4 | Account Rule Create/Update/Delete | - | - | - | - | - | A | - | R | - | - | - | - | -
6.1.5 | SQL Rules | - | - | - | - | - | A | C | R | - | - | - | - | -
6.1.6 | Job Template Amendment | - | - | - | - | - | A | R | - | - | - | - | - | -
6.1.7 | Job Schedules Core Create/Update/Delete | - | - | - | - | - | A | R | - | - | - | - | - | -
6.1.8 | Lodgement/Pay Points/Payment Codes Create/Update/Delete | - | - | - | - | - | A | R | - | - | - | - | - | -
6.2 | User/Access Control
6.2.1 | AD Group Set Up (Single Sign On) | bar: - to -
6.2.2 | User Create/Update/Delete (HeyCentric) | - | - | - | - | - | A | A | R | - | - | R | - | -
6.2.3 | User Create/Update/Delete (SyberNet) | - | - | - | - | - | A | A | R | - | - | R | - | -
6.2.4 | Data Constraint Role Amendments | - | - | - | - | - | A | C | R | - | - | - | - | -
6.2.5 | Menu Access Role Amendments | - | - | - | - | - | A | R | - | - | I | - | - | -
6.3 | Chip & PIN
6.3.1 | Chip & PIN Terminal Procurement (Raise Purchase Order & Complete Form) | - | - | - | - | - | I | - | - | - | I | R | - | -
6.3.2 | HeyCentric Set Up Lodgement/PayPoint/Refer to Supplier | - | - | - | - | - | A | R | - | - | I | - | - | -
6.3.3 | HeyCentric Configuration | - | - | - | - | - | A | - | - | - | - | - | R | -
6.3.4 | Terminal Network Setup | - | - | - | - | - | A | - | - | - | - | - | - | R
6.3.5 | User Training | - | - | - | - | - | A | - | - | - | R | I | - | -
6.3.6 | Maintain Chip & PIN terminal estate | - | - | - | - | - | I | - | - | - | R | - | - | -
6.4 | Third Party Integrations
6.4.1 | Supplier Engagement - Procurement / Non Technical | - | - | I | - | - | C | - | - | - | - | R | - | -
6.4.2 | Supplier Engagement - Technical | - | - | I | - | - | A | R | - | - | - | - | I | -
6.4.3 | HeyCentric Web Config (new pay points etc) | - | - | - | - | - | A | R | - | - | - | - | - | -
6.5 | System Controls
6.5.1 | Virtual Bank Reconcilation | - | - | - | - | C | C | C | - | R | - | - | - | -
6.5.2 | HC to ERP Gold Rec | - | - | - | - | C | C | C | - | R | - | - | - | -
6.6 | BAU Operations
6.6.1 | Suspense Allocation | bar: - - to - -
6.6.2 | Fund Transfer Templates | bar: - - to - -
6.6.3 | Cash & Cheque Template Import | bar: - - to - -; - I to - -
6.6.4 | Card Refunds | bar: - - to - -
6.6.5 | Disputes (Investigation, Evidencing and Reversal) | bar: - - to - -
6.6.6 | Dispute Reversals | - | - | - | - | - | A | R | - | - | - | - | - | -
6.6.7 | Reversals | - | - | - | - | - | A | C | R | - | I | - | - | -
6.6.8 | Payment Cross References | bar: - to -
6.6.9 | User Training | - | - | - | - | - | - | - | - | - | R | I | - | -
6.1.8 | Job Schedules Notifications Create/Update/Delete | - | - | - | - | - | A | C | R | - | - | - | - | -
6.7 | System Updates/Development
6.7.1 | Release Notes/Updates | - | - | I | I | I | C | I | I | - | I | - | R | -
6.7.2 | System Testing | bar: - to -
6.7.3 | Acceptance Testing | - | - | I | - | - | A | R | - | - | - | - | - | -
6.7.4 | TTL | - | I | C | I | C | A | R | I | I | - | - | - | -
6.7.5 | Task Matrix Changes | - | - | C | I | I | R | R | A | A | - | - | - | -
6.7.6 | Procedure Notes Update | - | - | I | - | - | C | R | I | I | - | - | - | -
6.7.7 | Procedure Notes Publishing | - | - | - | - | - | - | A | R | R | - | - | - | -
6.8 | Supplier Management & Contract Management
6.8.1 | Procurement / Re-procurement / Extension | I | A | R | I | C | C | I | I | I | - | - | I | I
6.8.2 | SLA / OLA Monitoring | - | A | R | - | I | I | - | - | - | - | - | C | C
6.8.3 | Compliance Requirements | - | A | I | I | R | C | - | - | - | - | - | C | C
6.8.4 | Environment Management | - | A | I | - | - | R | - | - | - | - | - | C | C